## Roadmap
Main Phases | Layer | Timeline | Workstream | Epic | Feature | Description | Key Users | Notes/Standard | Frontend Deliverables | API/Contracts | Backend Deliverables | DB Tables | Dependencies | Acceptable Criteria | Priority
Phase 1 | System Architecture and Technical Design | Week 1 | Backend Architecture (architecture-first) to match frontend contracts | System Architecture | Backend Layering + Service Boundaries | Define backend architecture: REST controllers → service layer → domain rules → repositories. Split core services: Auth/RBAC, Registry, QR/Badges, Subscriptions, Ledger, Payments/Webhooks, Meal Validation, Messaging, Dashboards/Reporting, Supplier Costs, AI/Alerts. Establish conventions for request_id, error codes, pagination, and school scoping. | Platform Admin; School Supervisor; Meal Server (Operator); Donor; Support | Project structure, module boundaries, shared middleware, request validation, standard response envelope. |  |  | Architecture documented and enforced by project structure + lint rules; all modules created with skeletons. |  |  | Architecture documented; modules skeletonized; lint rules enforce conventions. | P0
|  |  |  | API Routing & Standards | Endpoint Route Map + Versioning | Finalize complete route map (v1) and group by modules. Define versioning (/v1), consistent REST verbs, pagination (?page=&limit=), filtering, sorting, and error code catalog (e.g., NO_SUBSCRIPTION, ALREADY_SERVED, INVALID_QR, UNAUTHORIZED, FORBIDDEN). | All roles | Router setup, route grouping, OpenAPI spec generation, validation middleware, centralized error handler. |  | /v1/auth/*, /v1/users/*, /v1/schools/*, /v1/classes/*, /v1/children/*, /v1/plans/*, /v1/payments/*, /v1/webhooks/*, /v1/meal/*, /v1/dash/*, /v1/exports/*, /v1/messages/*, /v1/ai/* |  |  |  | Single authoritative OpenAPI spec exists and matches implemented routes; error code list published. | P0
|  |  |  | Security Model | Auth, RBAC, School Scoping, and PII Controls | Implement security model: JWT access tokens + refresh tokens, bcrypt/argon2 hashing, RBAC guards, mandatory school_id scoping for supervisors/operators, donor aggregate-only access, and PII minimization. Enforce least-privilege and audit all admin mutations. | Platform Admin; School Supervisor; Meal Server (Operator); Donor | Auth middleware, RBAC guards, query scoping helpers, donor-safe aggregation layer, audit middleware. |  | Applies to all endpoints; critical: /auth/*, /meal/validate, /dash/donor |  | users, roles, user_roles, login_logs, activity_logs |  | Attempted cross-school access returns FORBIDDEN; donor cannot access any PII endpoints; audit logs created. | P0
|  |  |  | Jobs, Workers, and Idempotency | Background Processing Blueprint | Define worker/job architecture: cron scheduler for subscription expiry + reminders, async processing for CSV import (optional), WhatsApp/SMS outbox worker, reconciliation job, AI report generation. Standardize idempotency keys (external_tx_id, client_request_id) and atomic transactions. | Platform Admin; Support | Job runner (cron/queue), retries with backoff, dead-letter handling, idempotency columns, transaction boundaries. |  | Internal: /jobs/*; Public: /meal/validate requires client_request_id; Webhook uses external_tx_id |  | message_outbox, message_logs, reconciliation_logs, validation_logs(client_request_id) |  | Workers run reliably in staging; retries do not duplicate ledger/subscription/serves. | P0
|  |  |  | Observability & Ops | Structured Logs + Monitoring + Backups | Implement structured logs (request_id, school_id, operator_id, child_id where allowed), centralized error tracking, health checks, and daily backups + restore drill. Add rate limiting and performance indexes for /meal/validate. | Platform Admin; Support | Logger middleware, /health endpoint, monitoring hooks, backup scripts, indexes, rate limiter. |  | GET /health; rate limit /meal/validate and /auth/* |  |  |  | Uptime monitoring active; backup restore tested; p95 scan endpoint target achieved with indexes. | P0
Phase 2 | Frontend Development | Week 2–4 | Frontend Development (UI-first build before backend integration) | UI Foundation & Architecture | Frontend System Architecture | Set up a production-ready frontend architecture: routing, role-based layouts, feature-based folder structure, shared component library (tables, forms, modals, toasts), API client abstraction, env config (staging/prod), error boundaries, loading/empty states, and typed contracts (OpenAPI → TS types). | Platform Admin; School Supervisor; Meal Server (Operator); Donor | Define API contracts only; use mock server/MSW for all endpoints; standardize error codes and pagination. | Repo bootstrap; design system; route guards; layout shells; global error/toast; mock data providers. | OpenAPI/Types for all endpoints; no live calls yet | N/A (UI-first) |  |  | You can click through the full app shell with mocked data; role-based navigation enforced. | P0
|  |  |  | Identity & Access (UI) | Login + Session UX | Implement login UI, session persistence, refresh handling, 401 interceptor, role-based redirect, and /me profile bootstrap. Include device-friendly UI for tablets used in schools. | Platform Admin; School Supervisor; Meal Server (Operator); Donor | Auth endpoints implemented later; define token strategy and secure storage assumptions. | Login page; protected routes; logout; session timeout UX. | POST /auth/login; POST /auth/refresh; GET /me (contract) | N/A |  |  | Login works end-to-end against mocks; refresh flow simulated; correct landing per role. | P0
|  |  |  | Admin Portal Screens | Registry Screens (Schools/Classes/Children) | Build Admin pages: Schools list/create/edit; Classes per school; Children list + filters + pagination; Child profile with tabs; Guardians editor; Enrollment change UI. Include consistent validation messages and audit-friendly UI patterns. | Platform Admin | Define CRUD payloads; list/filter standards; server-side pagination contracts. | Tables, forms, modals; CSV upload UI placeholder link; consistent empty/error states. | POST/GET/PATCH /schools; POST/GET/PATCH /classes; POST/GET/PATCH /children (contract) | N/A |  |  | All admin registry pages fully usable with mocks; form validation + pagination UX complete. | P0
|  |  |  | Bulk Operations (UI) | CSV Import UX + Reject Report | Implement CSV import UI: file upload, column mapping guidance, progress state, result summary (created/updated/rejected), and downloadable rejects CSV UI. Provide clear error display for invalid rows and duplicates. | Platform Admin | Define import response schema including reject reasons and report URL. | Upload component; progress and result tables; download rejects action. | POST /children/import; GET /children/import/:id/report (contract) | N/A |  |  | Admin can complete import flow end-to-end with mocks and see realistic summary + rejects. | P0
|  |  |  | QR Identity (UI) | QR Preview + Badge Print UX | Add QR preview on child profile; implement badge printing UI: select school/class, choose layout (A4/card), generate/download PDF, and print guidance. Include loading states and large-list performance considerations. | Platform Admin; School Supervisor | Define badge endpoint query params; PDF download headers; caching guidance. | QR preview component; print dialog; PDF download handler. | GET /children/:id/qr; GET /schools/:id/badges.pdf?class_id=&layout= (contract) | N/A |  |  | Admin can generate badge PDF (mock) for 300–1,000 children and download/print. | P0
|  |  |  | Subscriptions (UI) | Plans + Subscription Status Screens | Build Plans management UI (create/edit/activate/deactivate) and Child subscription view (status, meals remaining, end date). Add lists for children without active subscriptions for follow-up. | Platform Admin; School Supervisor | Define plan schema and subscription status payloads; filter/search contracts. | Plans CRUD pages; child subscription panel; list filters. | POST/GET/PATCH /plans; GET /children/:id/subscription (contract) | N/A |  |  | Plans and subscription status screens complete with mocks; entitlement state rendered clearly. | P0
|  |  |  | Ledger (UI) | Ledger Explorer UX (Admin) | Create ledger explorer with filters (child, school, date range, type), pagination, and export-ready view. Ensure donor never sees PII by design (separate donor dashboard). | Platform Admin | Define ledger query params, pagination and export contracts; define immutable event types. | Ledger table with filters; drill-down modal; export button placeholder. | GET /ledger/transactions?child_id=&school_id=&type=&date_from=&date_to= (contract) | N/A |  |  | Ledger explorer usable with mocked events; filters behave correctly. | P0
|  |  |  | Payments (UI) | Payment Link + Status UX | Implement payment intent UX: 'Send payment link' on child profile/list, show status (pending/paid/failed), display reference, and expose reconciliation widgets placeholders. Include copy-to-clipboard for links and references. | Platform Admin | Define payment intent schemas; webhook status projection fields; idempotency notes. | Payment modal; status badge; payments list; copy buttons. | POST /payments/intent; GET /payments/intent/:id (contract) | N/A |  |  | Admin can generate payment intent (mock) and see status updates (mock) in UI. | P0
|  |  |  | Supervisor Scanner PWA | Scanner UX + Operational Screens | Build scan screen with camera QR scanning (WebRTC), fast feedback (success/fail), reason code display, audio/vibration cues (optional), manual entry fallback, today totals, problems list, and meal history. Include offline banner + retry UX and client_request_id generation. | Meal Server (Operator); School Supervisor | Define validation reason codes; idempotency via client_request_id; performance target p95 < 300–500ms. | PWA routes: /scan, /today, /history; camera permissions; retry flow; install manifest (optional). | POST /meal/validate; GET /school/today; GET /meal/history?school_id=&date= (contract) | N/A |  |  | 300 continuous scans simulated; UI never freezes; duplicates and failures show correct messages. | P0
|  |  |  | Dashboards & UX States | Admin/School/Donor Dashboard UI | Build dashboards with KPI widgets, trend charts placeholders, and strict role-based visibility. Admin: revenue vs meals vs costs, expiring subs, scan failures. School: meals by class, failed scans, missing subs. Donor: aggregate-only metrics, no PII. Include CSV export UI. | Platform Admin; School Supervisor; Donor | Define dashboard endpoints and aggregation rules; donor masking rules; caching notes. | Dashboard pages + widgets; export buttons; consistent empty/loading/error UX. | GET /dash/admin; GET /dash/school; GET /dash/donor; GET /exports/monthly.csv (contract) | N/A |  |  | Dashboards render correctly with mocks; donor UI cannot navigate to any PII pages. | P0
Phase 3 | Backend Development | Week 4 - 8 | Secure foundation + core registry | Identity & Access | JWT Auth + Session Handling | Implement login + refresh token flow (JWT). Track login events. Enforce session expiry and token rotation rules suitable for production scanning devices and admin portal usage. | Platform Admin; School Supervisor; Meal Server (Operator) | Rate limits (basic); /me profile endpoint. |  | POST /auth/login; POST /auth/refresh; GET /me |  | users, roles, user_roles, login_logs | Phase 1 standards complete | Users can authenticate and access role-restricted endpoints. Login logs captured. | P0
|  |  | Secure foundation + core registry | RBAC | Roles + Permissions (ADMIN/SUPERVISOR/DONOR_READONLY + Operator) | Define roles and permission checks on all endpoints. Admin can create supervisors/operators and assign them to a single school context. Donor is strictly aggregate read-only. | Platform Admin; School Supervisor; Meal Server (Operator); Donor | Audit admin actions. |  | POST /users; PATCH /users/:id; GET /users; PATCH /users/:id/assign-school |  | users, roles, user_roles, activity_logs | JWT Auth ready | Supervisor/Operator can only see their assigned school data; Admin can manage all. | P0
|  |  | Core Registry | Core Registry | Schools CRUD | Create schools with unique codes, address, contacts, timezone, active flag. Use soft-delete rules. School is the top-level tenant for scoping most data. | Platform Admin | Uniqueness constraints; audit logs. |  | POST /schools; GET /schools; PATCH /schools/:id |  | schools, activity_logs | RBAC ready | Admin can create/update schools and list them. | P0
|  |  | Core Registry | Core Registry | Classes CRUD (per school) | Create classes under a school (e.g., Grade 3A). Ensure class belongs to one school. Support active/inactive. Used for badge printing and scan analytics. | Platform Admin; School Supervisor | Enforce school_id ownership; audit logs. |  | POST /schools/:id/classes; GET /schools/:id/classes; PATCH /classes/:id |  | classes, schools, activity_logs | Schools CRUD | Classes can be created and reliably linked to the right school. | P0
|  |  | Core Registry | Core Registry | Children + Guardians + Enrollment | Model children with unique student_id, names, DOB/grade fields, class_id, status (active/inactive). Link 1..N guardians with phone, preferred channel (WhatsApp/SMS), and relationship. Keep enrollment history for class changes. | Platform Admin; School Supervisor | Enrollment history on class change; strong validation. |  | POST /children; GET /children; PATCH /children/:id; POST /children/:id/guardians; PATCH /guardians/:id |  | children, guardians, enrollment_history | Schools + Classes exist | Child records and guardians can be created/updated; class changes create enrollment_history entries. | P0
|  |  | Bulk Operations | Bulk Operations | CSV Import Children (500+ per school) | Implement CSV upload parsing with robust validation (required columns, duplicates, invalid class mapping). Provide import summary: created, updated, rejected rows with reasons. Support idempotent re-import by student_id. | Platform Admin | Background job optional; import report; audit log. |  | POST /children/import; GET /children/import/:id/report |  | children, guardians, enrollment_history, activity_logs | Children model + Classes | Admin can import 500+ children in one operation with clear error reporting. | P0
|  |  | Audit & Logging | Audit & Logging | Activity Logs (Admin actions) | Append audit logs for admin actions: user created, school created, import executed, plan created, manual adjustments. Store who/what/when + before/after snapshot metadata. | Platform Admin; Support | Audit middleware; searchable logs. |  | GET /audit/activity?actor_id=&entity=&date_from=&date_to= |  | activity_logs | RBAC + Auth | All admin mutations create an activity log entry; logs are searchable. | P1
|  |  | QR Identity | QR Identity | QR Payload + Auto-Generation | QR encodes pointer only: SMMS-<student_id>. On child create/import, generate payload and (optionally) a QR image file. Store payload + QR asset URL. Ensure no PII is encoded. | Platform Admin; School Supervisor; Meal Server (Operator) | Use storage integration (S3/local). |  | GET /children/:id/qr |  | child_qr (child_id, qr_payload, qr_image_url, created_at) | Children exist | All children have QR payload generated; scanning reveals student_id pointer only. | P0
|  |  | Badge Printing | Badge Printing | Badge PDF Export (A4 sheets / cards) | Generate printable PDFs: per class or school. Include child name, student_id, class, QR code, and optionally school logo. Support A4 multi-badge sheet and single-card layout. Include pagination and print-safe margins. | Platform Admin | Cache PDFs where appropriate; print-safe layouts. |  | GET /schools/:id/badges.pdf?class_id=&layout=a4¦card |  | child_qr, children, classes, schools | QR generated | 300–1,000 badges print reliably; PDF loads quickly and consistently. | P0
|  |  | Subscriptions | Subscriptions | Subscription Plans (CRUD) | Create subscription plans: name, meal_type, meals_per_cycle, price, active flag, effective dates. Plans drive entitlements and pricing for purchases and serving. | Platform Admin | Versioning optional; audit logs. |  | POST /plans; GET /plans; PATCH /plans/:id |  | subscription_plans, activity_logs | Registry ready | Admin can manage plans; inactive plans cannot be purchased. | P0
|  |  | Subscriptions | Subscriptions | Child Subscription State | Child subscription tracks status (ACTIVE/EXPIRED/CANCELLED), start/end date, meals_remaining, meal_type. Support renewals (new cycle) and early cancellation rules. Include daily expiry job. | Platform Admin; School Supervisor | Expiry cron/job required. |  | GET /children/:id/subscription; (internal) POST /jobs/expire-subscriptions |  | child_subscriptions | Plans exist | Subscription status and meals_remaining behave correctly across date changes. | P0
|  |  | Ledger | Ledger | Immutable Transactions (Append-only) | Implement append-only ledger table for financial/entitlement events: SUBSCRIPTION_PURCHASE, DEBIT_MEAL, ADJUSTMENT. No updates/deletes allowed; corrections are new transactions. Include filters by child, school, date, type. | Platform Admin; Donor; Support | Insert-only constraints; donor-safe aggregates only. |  | GET /ledger/transactions?child_id=&school_id=&type=&date_from=&date_to= |  | transactions | Subscription engine | Ledger shows purchase/debits; immutability enforced at DB level. | P0
|  |  | Ops Tools | Ops Tools | Manual Attach Subscription (Admin) | Admin can attach a subscription to a child for testing/pilot (or offline cash conversion) with mandatory reason note. Must write ledger entry SUBSCRIPTION_PURCHASE and activity log. | Platform Admin | Admin-only endpoint with required reason field. |  | POST /children/:id/subscription/manual |  | child_subscriptions, transactions, activity_logs | Ledger ready | Admin can activate subscription and ledger reflects it correctly. | P1
|  |  | Payments | Payments | Payment Intent Creation | Create payment intents: child_id, plan_id, amount, reference (SMMS-SUB-<child_id>-<plan_id>-<yyyymm>), status. Return payment_url from aggregator. | Platform Admin; Parent/Guardian | Enforce idempotency; store reference. |  | POST /payments/intent; GET /payments/intent/:id |  | payment_intents | Plans + children exist | Payment link generated and stored; reference is unique and traceable. | P0
|  |  | Payments | Payments | Webhook Processing (HMAC + Idempotency) | Implement webhook endpoint from aggregator. Verify signature/HMAC. Use external_tx_id as idempotency key. On success: record payment_event, create/renew child_subscription (ACTIVE), insert SUBSCRIPTION_PURCHASE ledger entry. Prevent replay. | Platform Admin; Parent/Guardian | Atomic transaction; prevent replay. |  | POST /webhooks/aggregator |  | payment_events, child_subscriptions, transactions | Payment intents | Real payment triggers ACTIVE subscription; repeated webhook does not duplicate records. | P0
|  |  | Reconciliation | Reconciliation | Daily Totals + Mismatch Flags | Compute daily totals: payments received vs subscriptions activated vs meals served. Store summaries and mismatch warnings for admin review. | Platform Admin | Reconciliation job; summaries endpoint; alerts optional. |  | GET /reconciliation/daily?date= |  | reconciliation_logs | Webhook live | Admin can see daily totals and quickly identify inconsistencies. | P1
|  |  | Meal Validation | Meal Validation | POST /meal/validate (Atomic) | Validation steps: child exists+active; belongs to school; has ACTIVE subscription for meal_type; valid today; meals_remaining>0; not already served today for same meal_type (double-scan protection). On success: insert meal_serves, decrement meals_remaining, insert DEBIT_MEAL ledger entry. Log every attempt with reason codes. | Meal Server (Operator); School Supervisor; Platform Admin | DB transaction; reason codes; indexes for speed. |  | POST /meal/validate; GET /school/today; GET /meal/history?school_id=&date= |  | meal_serves, validation_logs, child_subscriptions, transactions | Subscriptions + QR + Auth | 300 consecutive scans succeed quickly; duplicates blocked; reasons shown for failures. | P0
|  |  | Offline/Resilience | Offline/Resilience | Graceful Failures + Retry Strategy | Define operator UX for network issues: queue failed requests (optional), show clear error states, and allow manual retry. Ensure no double-debit on retries via request idempotency key (client_request_id). | Meal Server (Operator) | Idempotency on /meal/validate; optional client queue. |  | POST /meal/validate (with client_request_id) |  | validation_logs (store client_request_id) | Meal validation | Retries do not create duplicate debits; operator understands what happened. | P1
|  |  | Messaging | Messaging | Outbox + Worker (WhatsApp Cloud API) | Adopt outbox pattern: write message jobs to message_outbox. Worker sends via WhatsApp Cloud API; on failure fallback to SMS provider. Log delivery attempts, retries, and hard failures. | Parent/Guardian; Platform Admin | Retry policy; delivery logs. |  | GET /messages/health (admin); internal enqueue on events |  | message_outbox, message_logs | Payments + subscriptions | Payment success triggers confirmation message to guardian; daily reminder job sends messages. | P0
|  |  | Messaging | Messaging | Event Triggers + Templates | Templates for: subscription activated; expiring soon (T-3); expired; (optional) meal served. Include opt-out toggle at guardian or school level. Keep messages concise and privacy-safe. | Parent/Guardian; Platform Admin; School Supervisor | Template system; scheduler job; preference flags per guardian. |  | (internal) POST /jobs/send-expiry-reminders |  | guardians, message_outbox | Outbox worker | Expiry reminders run daily and message statuses are tracked. | P1
|  |  | Suppliers | Suppliers | Supplier Registry + Invoices | Create suppliers and track invoices per school/month. Capture invoice amount, due date, status, and payments. Enable cost per meal calculation: total supplier cost / meals served for period. | Platform Admin; School Supervisor; Supplier/Vendor | Cost/meal calculation endpoints. |  | POST/GET /suppliers; POST/GET /invoices; POST /invoices/:id/pay |  | suppliers, supplier_invoices, supplier_payments | Meal serving + ledger | Admin can track supplier costs and compute cost per meal monthly. | P0
|  |  | Dashboards | Dashboards | Admin Dashboard (KPIs + Exports) | KPIs: meals today/month, active subscriptions, expiring soon, revenue month, supplier cost month, cost/meal, scan failure reasons. Provide CSV exports by school/month. | Platform Admin | Caching recommended; export endpoints. |  | GET /dash/admin; GET /exports/monthly.csv?school_id=&month= |  | derived from transactions, meal_serves, child_subscriptions, supplier_invoices | Suppliers + serving | Admin can reconcile revenue vs meals vs costs and export monthly CSV. | P0
|  |  | Dashboards | Dashboards | School Dashboard (Daily Ops) | Daily meals by class, list of failed scans with reason codes, children missing subscriptions, and quick links to guardian contact for payment follow-up. | School Supervisor; Meal Server (Operator) | School-scoped aggregations only. |  | GET /dash/school |  | derived from meal_serves, validation_logs, children, classes, subscriptions | Validation logs | Supervisor can manage daily operations and resolve issues quickly. | P0
|  |  | Dashboards | Dashboards | Donor Read-only Dashboard (Aggregate) | Provide donor-safe aggregates only (no names/phones): total meals served, children reached, funds received (aggregate), cost/meal, trend charts. Enforce RBAC + aggregation-only queries. | Donor | Strict masking rules; no PII endpoints. |  | GET /dash/donor |  | aggregations from transactions + meal_serves + schools | RBAC donor role | Donor sees safe aggregates only; no PII accessible. | P0
|  |  | AI (Light) | AI (Light) | 7-day Meal Forecast + Alerts | Forecast meals for next 7 days (moving average baseline). Create anomaly alerts: meal spikes vs baseline, high no-subscription scan attempts, payments vs meals mismatch. Produce weekly executive summary (LLM) using aggregates only. | Platform Admin; Donor (summary); School Supervisor | Aggregates only; no PII in prompts. |  | GET /ai/forecast?school_id=; GET /ai/alerts; GET /ai/reports/weekly |  | anomaly_alerts, ai_reports | Dashboards data available | Weekly summary and actionable alerts generated without exposing PII. | P1
Phase 4 | Integration & Testing | Week 8 | E2E Integration | Integration | Remove Mocks + Connect UI to API | Switch frontend from MSW mocks to live staging API. Validate all flows: onboarding, badge print, payments→subscription, scanning→deduction, dashboards, donor masking. | All roles | Focus on end-to-end reliability; verify error codes match UI states. | Frontend fully integrated; no mocks; bug fixes. | All implemented endpoints | E2E test suite; regression fixes; API contract alignment. |  | Phase 2 + Phase 3 complete | System works end-to-end in staging; all critical flows validated. | P0
|  |  | Testing | Performance & Security Testing | Load + Replay + Pen Tests | Run load tests for /meal/validate (scan bursts), webhook replay/idempotency tests, role-based access tests (cross-school), donor PII restrictions, CSV large-file tests, and backup restore drill in staging. | Platform Admin; Support | Measure p95 latency for validation; confirm no duplicate debits; verify backups restore correctly. |  |  | Test reports; tuned indexes; fixed bottlenecks; patched security gaps. |  | Phase 3 complete; staging ready | All tests pass; scan endpoint meets latency target; idempotency verified; donor PII blocked. | P0
Phase 5 | Deployment & DevOps | Week 8 | DevOps | CI/CD & Environments | Staging/Prod Setup + Secrets + Monitoring | Set up CI/CD, environment configs, secrets management, SSL, domains, structured logging, monitoring/alerting, and automated backups. Harden rate limiting and request size limits. | Platform Admin; Support | Production hardening and observability. |  | GET /health (ops), deploy pipeline | Production deploy playbook; monitoring dashboards; alert rules; backup schedules. |  | Phase 4 passed | Production deployment is repeatable; monitoring and backups are active; incident response basics defined. | P0

## API_Index
Endpoint | Method | Purpose | Auth Role(s) | Notes (Idempotency/Validation)
/auth/login | POST | Login and return access/refresh tokens | ADMIN/SUPERVISOR/OPERATOR/DONOR | Rate limit; store login_logs
/auth/refresh | POST | Refresh tokens | All authenticated | Rotate refresh token; detect reuse
/me | GET | Return current user profile and scope | All authenticated | Include school assignment
/schools | POST/GET | Create and list schools | ADMIN | Soft delete
/schools/:id | PATCH | Update school | ADMIN | Audit log
/schools/:id/classes | POST/GET | Create/list classes per school | ADMIN; SUPERVISOR read | Enforce school scope
/children | POST/GET | Create/list children | ADMIN; SUPERVISOR read | Filter by school scope
/children/:id | PATCH | Update child | ADMIN | Enrollment history on class change
/children/import | POST | Bulk import children | ADMIN | Return report; idempotent by student_id
/children/:id/qr | GET | Fetch QR payload/image for a child | ADMIN/SUPERVISOR | No PII in QR
/schools/:id/badges.pdf | GET | Download printable badges PDF | ADMIN | Support layout parameter
/plans | POST/GET | Create/list subscription plans | ADMIN | Active flag
/plans/:id | PATCH | Update plan | ADMIN | Audit log
/children/:id/subscription | GET | Read child's subscription status | ADMIN/SUPERVISOR | No donor access
/ledger/transactions | GET | Query ledger | ADMIN (child-level), DONOR (aggregate-only via different view) | Append-only; block updates/deletes
/payments/intent | POST | Create payment intent and return payment_url | ADMIN | Reference SMMS-SUB-...
/payments/intent/:id | GET | Fetch intent status | ADMIN | Pending/paid
/webhooks/aggregator | POST | Process payment webhooks | N/A | Verify HMAC; idempotent by external_tx_id
/meal/validate | POST | Validate scan and debit meal entitlement | OPERATOR/SUPERVISOR | Atomic; client_request_id idempotency; double-scan block
/school/today | GET | Daily totals for school | SUPERVISOR/OPERATOR | Fast aggregation
/meal/history | GET | Meal serve history | SUPERVISOR | Filter by date
/messages/health | GET | Message delivery health stats | ADMIN | Counts pending/sent/failed
/suppliers | POST/GET | Manage suppliers | ADMIN | Supplier login optional later
/invoices | POST/GET | Create/list invoices | ADMIN | School/month scoping
/invoices/:id/pay | POST | Mark invoice paid | ADMIN | Ledger entry optional
/dash/admin | GET | Admin KPIs | ADMIN | Use caching where needed
/dash/school | GET | School KPIs | SUPERVISOR | School-scoped
/dash/donor | GET | Donor aggregates | DONOR_READONLY | No PII
/ai/forecast | GET | 7-day meal forecast | ADMIN/SUPERVISOR | Aggregate only
/ai/alerts | GET | Anomaly alerts | ADMIN | Severity + status
/ai/reports/weekly | GET | Weekly executive summary | ADMIN/DONOR (safe version) | LLM uses aggregates only

## Data_Model
Entity/Table | Core Fields (suggested) | Relationships | Notes
users | id, email/username, password_hash, status, created_at | M:N with roles via user_roles; optional belongs_to school via assignment | Store minimal PII; enforce strong hashing
roles | id, name | M:N users | ADMIN, SUPERVISOR, OPERATOR, DONOR_READONLY
user_roles | user_id, role_id | Join table | Index by user_id
login_logs | id, user_id, ip, user_agent, created_at | Many per user | Useful for security
schools | id, name, code, address, active, created_at | 1:N classes; 1:N children; 1:N invoices | Tenant boundary for scoping
classes | id, school_id, name, grade, active | Belongs to school; 1:N children | Index on school_id
children | id, school_id, class_id, student_id(unique), first_name, last_name, status | Belongs to school/class; 1:N guardians; 1:1 child_qr; 1:N subscriptions | student_id must be unique at least per system
guardians | id, child_id, name, phone, preferred_channel, active | Belongs to child | Phone is key for messaging
enrollment_history | id, child_id, from_class_id, to_class_id, changed_at, changed_by | Tracks class changes | For audits
activity_logs | id, actor_user_id, action, entity_type, entity_id, metadata_json, created_at | Admin audit trail | Append-only preferred
child_qr | child_id, qr_payload, qr_image_url, created_at | 1:1 child | QR pointer only
subscription_plans | id, name, meal_type, meals_per_cycle, price, active | 1:N child_subscriptions | Keep price history if needed
child_subscriptions | id, child_id, plan_id, status, start_date, end_date, meals_remaining | Belongs to child/plan | Renew by creating new record or updating with history (choose one)
transactions | id, child_id, school_id, type, amount, meal_type, reference, created_at, metadata_json | Append-only ledger | No update/delete; corrections via new rows
payment_intents | id, child_id, plan_id, amount, reference, status, payment_url, created_at | 1:N payment_events | One per cycle recommended
payment_events | id, external_tx_id, intent_id, status, raw_payload_json, received_at | Webhook records | external_tx_id must be unique
reconciliation_logs | date, school_id, payments_total, meals_total, mismatches_json | Daily aggregates | Useful for finance control
meal_serves | id, child_id, school_id, meal_type, serve_date, served_at, operator_id | One per meal per day | Unique (child_id, meal_type, serve_date) to block duplicates
validation_logs | id, child_id, school_id, operator_id, result, reason_code, client_request_id, created_at | All attempts | For troubleshooting and fraud detection
message_outbox | id, guardian_id, channel, template, payload_json, status, tries, next_retry_at | Worker processes | Outbox pattern
message_logs | id, outbox_id, provider, provider_msg_id, status, error, sent_at | Delivery trace | Keep for audits
suppliers | id, name, contact, phone, email, active | 1:N invoices | Supplier portal optional later
supplier_invoices | id, supplier_id, school_id, month, amount, status, due_date | 1:N payments | Basis for cost per meal
supplier_payments | id, invoice_id, amount, paid_at, method, reference | Belongs to invoice | Reconcile with ledger if needed
anomaly_alerts | id, school_id, type, severity, details_json, created_at, status | Alerts feed dashboard | Aggregate-only
ai_reports | id, school_id, week_start, report_text, generated_at | Weekly summaries | Do not include PII

## Other requirements
Category | Requirement / Standard | Implementation Notes
Security | Password hashing + JWT best practices | Use strong hashing (bcrypt/argon2). Rotate refresh tokens. Store secrets in env/secret manager.
Security | RBAC + School-scoping hard rules | Every query must be scoped to school_id for non-admin roles; test with negative cases.
Security | Webhook signature verification + idempotency | Verify HMAC from aggregator; unique external_tx_id; atomic DB transaction.
Security | PII minimization + donor-safe aggregates | Never expose child/guardian info to donor role; QR contains pointer only.
Performance | Scan endpoint p95 latency target | Aim p95 < 300ms at pilot load; add indexes and avoid heavy joins.
Reliability | Atomic transactions for serve debit | meal_serves + decrement meals_remaining + ledger insert in one DB tx.
Reliability | Backup + restore testing | Daily backups + periodic restore drill; document RPO/RTO.
Observability | Structured logs + error monitoring | Log request_id, operator_id, school_id. Add uptime checks and error tracking.
Deployment | Staging + production environments | Separate env variables and DBs. Use migrations. Provide deployment playbook.
Compliance | Audit trail for admin actions | Append-only activity logs; protect from tampering; exportable.

## Key_Users
User Type | Role Code | Description | Core Responsibilities | System Functionalities | Data Scope & Restrictions
Children (Beneficiaries) | CHILD | Children are the registered beneficiaries of the school meals program and represent the core entitlement unit. Each child has a unique student ID and QR badge used for secure meal validation. Meals are granted only when an active subscription exists, and entitlement automatically decreases after each validated scan. Their records connect guardians, classes, and schools for operational and financial tracking. | Present QR badge; trigger entitlement validation; generate meal serve records. | QR identity; subscription tracking; meal validation engine; enrollment linkage. | No login access. Data visible only to authorized school and program staff.
Parents / Guardians | GUARDIAN | Parents or guardians finance the child’s monthly meal subscription. They interact primarily through secure payment links delivered via WhatsApp or SMS. After successful payment, subscriptions activate automatically and confirmation messages are sent. Guardians receive reminders before expiration and alerts when subscriptions lapse, ensuring continuity and financial sustainability of the program. | Initiate subscription payments; receive confirmations and reminders; maintain payment continuity. | Payment intent link; mobile money checkout; notification engine; subscription activation. | No portal access in MVP. Identified via verified phone number only.
School Administration (Supervisors / Agents) | SUPERVISOR / OPERATOR | School administrators and meal agents manage daily meal distribution within their assigned school. They scan QR badges, validate eligibility, prevent duplicate serving, monitor real-time meal totals, and review failed scans. Access is strictly limited to their school, ensuring localized operational control, accountability, and secure data boundaries. | Operate scanner; validate entitlement; monitor daily totals; escalate unpaid cases. | Scanner PWA; school dashboard; meal history; failure reason tracking. | Restricted to assigned school only. Cannot modify pricing or global settings.
Suppliers | SUPPLIER | Suppliers provide food and related services to participating schools and form the operational cost base of the program. They issue invoices based on delivered meals or agreements. In the MVP, supplier records and invoices are managed by program administrators to ensure structured cost tracking, reconciliation, and cost-per-meal transparency. | Deliver food; submit invoices; support reconciliation process. | Supplier registry; invoice tracking; cost-per-meal analytics. | No independent login in MVP. Managed entirely by Program Administration.
Program Administration | ADMIN | Program administrators oversee the entire platform across all schools. They configure schools, plans, subscriptions, payments, suppliers, messaging, dashboards, and reports. They ensure financial integrity, audit compliance, operational performance, and transparency. Administrators reconcile revenue against meals served and manage alerts, forecasting, and governance controls. | Full system governance; configure plans; reconcile payments; audit ledger; manage suppliers; monitor dashboards. | Admin portal; ledger explorer; reconciliation tools; exports; AI alerts. | Global cross-school access. All actions logged. No hard deletes permitted.
Donors | DONOR_READONLY | Donors access aggregate performance metrics to monitor impact, financial transparency, and operational efficiency. They review total meals served, children reached, funds received, cost-per-meal ratios, and trends over time. Donors never access personally identifiable information or child-level financial data, preserving privacy while supporting accountability and funding evaluation. | Review aggregate impact metrics; analyze trends; evaluate funding efficiency. | Donor dashboard; aggregate KPIs; executive summaries; trend charts. | Strictly read-only. No PII or child-level access permitted.